## Summary
Hummer Production Push – Phase 1 Ticket Analysis
Source: HubSpot CRM Export ¦ Date: 2026-06-06 ¦ Total Tickets: 76
KEY METRICS
Total Tickets | Unique Jobs | Duplicate Tickets | Marked No Customer | Has Customer, Missing CRM | Jobs w/ Duplicates
76 | 49 | 27 | 55 | 9 | 13
TICKETS BY OWNER |  |  |  | TICKETS BY STAGE
Owner | Ticket Count | % of Total |  | Stage | Count | % of Total
Fraser Finlayson | 40 | 52.63% |  | Interior Linings | 13 | 17.11%
Andrew Scott | 16 | 21.05% |  | Painting & Finishing | 11 | 14.47%
Killian O'Neill | 13 | 17.11% |  | Schedule Pre Construction Meeting | 9 | 11.84%
Corey Flynn | 7 | 9.211% |  | Fixtures/Internal Fit Out | 8 | 10.53%
Total | 76 | 100% |  | Cladding On | 6 | 7.895%
|  |  |  | Roof On | 5 | 6.579%
|  |  |  | Contract Confirmed Signed | 4 | 5.263%
|  |  |  | Customer Walkthrough & Final Inspection | 4 | 5.263%
|  |  |  | Foundations / Slab Poured | 4 | 5.263%
|  |  |  | Schedule Handover | 4 | 5.263%
|  |  |  | WD Submitted to Council | 3 | 3.947%
|  |  |  | Groundwork Commenced | 2 | 2.632%
|  |  |  | Frames Up | 2 | 2.632%
|  |  |  | Windows In | 1 | 1.316%

## Duplicates
Duplicate Tickets — Hummer Phase 1
13 job numbers have duplicate tickets. 40 tickets total → 27 extras to delete. All duplicates owned by Fraser Finlayson.
Job Number | Ticket ID | Ticket Name | Stage | Owner | Action
CT7509a | 258562793931 | CT7509a (Townhouse 4, 51 Monsaraz Boulevard, Halswell Commons) | Schedule Handover | Fraser Finlayson | KEEP (oldest)
CT7509a | 258635160040 | CT7509a (Townhouse 4, 51 Monsaraz Boulevard, Halswell Commons) | Schedule Handover | Fraser Finlayson | DELETE
CT7509a | 258642362831 | CT7509a (Townhouse 4, 51 Monsaraz Boulevard, Halswell Commons) | Schedule Handover | Fraser Finlayson | DELETE
CT7509a | 258575416814 | CT7509a (Townhouse 4, 51 Monsaraz Boulevard, Halswell Commons) | Schedule Handover | Fraser Finlayson | DELETE
CT8196 | 258642367949 | CT8196 (Lot 8 Te Whaiawa - 76 Te Whaiawa Crescent, West Melton) | Painting & Finishing | Fraser Finlayson | KEEP (oldest)
CT8196 | 258516061676 | CT8196 (Lot 8 Te Whaiawa - 76 Te Whaiawa Crescent, West Melton) | Painting & Finishing | Fraser Finlayson | DELETE
CT8196 | 258642361821 | CT8196 (Lot 8 Te Whaiawa - 76 Te Whaiawa Crescent, West Melton) | Painting & Finishing | Fraser Finlayson | DELETE
CT8197 | 258553799140 | CT8197 (Lot 9 Te Whaiawa - 74 Te Whaiawa Crescent, West Melton) | Painting & Finishing | Fraser Finlayson | KEEP (oldest)
CT8197 | 258644182479 | CT8197 (Lot 9 Te Whaiawa - 74 Te Whaiawa Crescent, West Melton) | Painting & Finishing | Fraser Finlayson | DELETE
CT8197 | 258645983696 | CT8197 (Lot 9 Te Whaiawa - 74 Te Whaiawa Crescent, West Melton) | Painting & Finishing | Fraser Finlayson | DELETE
CT8200 | 258544874995 | CT8200 (Lot 14 Te Whaiawa - 64 Te Whaiawa Crescent, West Melton) | Interior Linings | Fraser Finlayson | KEEP (oldest)
CT8200 | 258642366950 | CT8200 (Lot 14 Te Whaiawa - 64 Te Whaiawa Crescent, West Melton) | Interior Linings | Fraser Finlayson | DELETE
CT8200 | 258644177345 | CT8200 (Lot 14 Te Whaiawa - 64 Te Whaiawa Crescent, West Melton) | Interior Linings | Fraser Finlayson | DELETE
CT8203 | 258580864502 | CT8203 (Lot 17 Te Whaiawa - 58 Te Whaiawa Crescent, West Melton, Selwyn) | Interior Linings | Fraser Finlayson | KEEP (oldest)
CT8203 | 258645991877 | CT8203 (Lot 17 Te Whaiawa - 58 Te Whaiawa Crescent, West Melton, Selwyn) | Interior Linings | Fraser Finlayson | DELETE
CT8203 | 258635154881 | CT8203 (Lot 17 Te Whaiawa - 58 Te Whaiawa Crescent, West Melton, Selwyn) | Interior Linings | Fraser Finlayson | DELETE
CT8204 | 258566393307 | CT8204 (Lot 18 Te Whaiawa - 56 Te Whaiawa Crescent, West Melton) | Cladding On | Fraser Finlayson | KEEP (oldest)
CT8204 | 258635160042 | CT8204 (Lot 18 Te Whaiawa - 56 Te Whaiawa Crescent, West Melton) | Cladding On | Fraser Finlayson | DELETE
CT8204 | 258562787775 | CT8204 (Lot 18 Te Whaiawa - 56 Te Whaiawa Crescent, West Melton) | Cladding On | Fraser Finlayson | DELETE
CT8426 | 258647787966 | CT8426 (Lot 11 Halswell Country Estates - 45 Podocarp Drive, Christchurch) | Fixtures/Internal Fit Out | Fraser Finlayson | KEEP (oldest)
CT8426 | 258644182482 | CT8426 (Lot 11 Halswell Country Estates - 45 Podocarp Drive, Christchurch) | Fixtures/Internal Fit Out | Fraser Finlayson | DELETE
CT8426 | 258638765539 | CT8426 (Lot 11 Halswell Country Estates - 45 Podocarp Drive, Christchurch) | Fixtures/Internal Fit Out | Fraser Finlayson | DELETE
CT8427 | 258642367950 | CT8427 (Lot 12 Halswell Country Estates - 47 Podocarp Drive, Christchurch) | Fixtures/Internal Fit Out | Fraser Finlayson | KEEP (oldest)
CT8427 | 258644182483 | CT8427 (Lot 12 Halswell Country Estates - 47 Podocarp Drive, Christchurch) | Fixtures/Internal Fit Out | Fraser Finlayson | DELETE
CT8427 | 258575416816 | CT8427 (Lot 12 Halswell Country Estates - 47 Podocarp Drive, Christchurch) | Fixtures/Internal Fit Out | Fraser Finlayson | DELETE
CT8428 | 258580864503 | CT8428 (Lot 13 Halswell Country Estates - 49 Podocarp Drive, Christchurch) | Customer Walkthrough & Final Inspection | Fraser Finlayson | KEEP (oldest)
CT8428 | 258516061679 | CT8428 (Lot 13 Halswell Country Estates - 49 Podocarp Drive, Christchurch) | Customer Walkthrough & Final Inspection | Fraser Finlayson | DELETE
CT8428 | 258638765540 | CT8428 (Lot 13 Halswell Country Estates - 49 Podocarp Drive, Christchurch) | Customer Walkthrough & Final Inspection | Fraser Finlayson | DELETE
CT8554 | 258544874996 | CT8554 (Lot 30 Quaifes Park - 39 Cork Street, Halswell, Christchurch) | Interior Linings | Fraser Finlayson | KEEP (oldest)
CT8554 | 258553798129 | CT8554 (Lot 30 Quaifes Park - 39 Cork Street, Halswell, Christchurch) | Interior Linings | Fraser Finlayson | DELETE
CT8554 | 258562787776 | CT8554 (Lot 30 Quaifes Park - 39 Cork Street, Halswell, Christchurch) | Interior Linings | Fraser Finlayson | DELETE
CT8555 | 258575424978 | CT8555 (Lot 31 Quaifes Park - 41 Cork Street, Halswell, Christchurch) | Interior Linings | Fraser Finlayson | KEEP (oldest)
CT8555 | 258635160043 | CT8555 (Lot 31 Quaifes Park - 41 Cork Street, Halswell, Christchurch) | Interior Linings | Fraser Finlayson | DELETE
CT8555 | 258644177346 | CT8555 (Lot 31 Quaifes Park - 41 Cork Street, Halswell, Christchurch) | Interior Linings | Fraser Finlayson | DELETE
CT8587 | 258544874997 | CT8587 (Lot 16 Sabys Estate - 36 Matamoe Drive, Halswell) | Roof On | Fraser Finlayson | KEEP (oldest)
CT8587 | 258645991883 | CT8587 (Lot 16 Sabys Estate - 36 Matamoe Drive, Halswell) | Roof On | Fraser Finlayson | DELETE
CT8587 | 258644177347 | CT8587 (Lot 16 Sabys Estate - 36 Matamoe Drive, Halswell) | Roof On | Fraser Finlayson | DELETE
CT8617 | 258541256156 | CT8617 (Lot 17 Halswell Country Estates - 20 Podocarp Drive, Halswell) | WD Submitted to Council | Fraser Finlayson | KEEP (oldest)
CT8617 | 258705226199 | CT8617 (Lot 17 Halswell Country Estates - 20 Podocarp Drive, Halswell) | WD Submitted to Council | Fraser Finlayson | DELETE
CT8617 | 258638765542 | CT8617 (Lot 17 Halswell Country Estates - 20 Podocarp Drive, Halswell) | WD Submitted to Council | Fraser Finlayson | DELETE

## No Customer
Tickets Marked 'No Customer' (55 of 76)
Ticket ID | Ticket Name | Hummer Job # | Owner | Stage | Has Contact | Has Deal
258635161035 | CT8669 (Lot 36 Grayshott Glade - 10 Tulett Park Drive, Casebrook, Christchurch) | CT8669 | Killian O'Neill | Contract Confirmed Signed | Yes | No
258638773735 | CT8668 (Lot 35 Grayshott Glade - 8 Tulett Park Drive, Casebrook, Christchurch) | CT8668 | Killian O'Neill | Contract Confirmed Signed | Yes | No
258516062697 | CT8667 (Lot 32 Grayshott Glade - 6 Komanawa Place, Casebrook, Christchurch) | CT8667 | Killian O'Neill | Contract Confirmed Signed | Yes | No
258580865469 | CT8666 (Lot 31 Grayshott Glade - 8 Komanawa Place, Casebrook, Christchurch) | CT8666 | Killian O'Neill | Contract Confirmed Signed | Yes | No
258645992904 | CT8410 (Lot 6 Highsted - 64 Flaxmill Road, Casebrook) | CT8410 | Killian O'Neill | Cladding On | Yes | No
258516062696 | CT8374 (Lot 245 Silverstream - 35 Bastings Street, Kaiapoi) | CT8374 | Killian O'Neill | Schedule Pre Construction Meeting | Yes | No
258516062695 | CT8373 (Lot 244 Silverstream - 37 Bastings Street, Kaiapoi) | CT8373 | Killian O'Neill | Groundwork Commenced | Yes | No
258564590019 | CT8372 (Lot 24 Silverstream - 57 Adderley Terrace, Kaiapoi) | CT8372 | Killian O'Neill | Painting & Finishing | Yes | No
258647787970 | CT8371 (Lot 23 Silverstream - 35 Joslen Way, Kaiapoi) | CT8371 | Killian O'Neill | Schedule Pre Construction Meeting | Yes | No
258541256161 | CT8370 (Lot 22 Silverstream - 61 Adderley Terrace, Kaiapoi) | CT8370 | Killian O'Neill | Schedule Pre Construction Meeting | Yes | No
258642367952 | CT8369 (Lot 139 Silverstream - 48 Adderley Terrace, Kaiapoi) | CT8369 | Killian O'Neill | Customer Walkthrough & Final Inspection | Yes | No
258638773734 | CT8405 (Lot 140 Prestons Grove - 25 Padstow Loop, Marshland, Christchurch) | CT8405 | Andrew Scott | Schedule Pre Construction Meeting | Yes | No
258575424980 | CT8391 (Lot 19 Prestons Grove - 11 Padstow Loop, Marshland, Christchurch) | CT8391 | Andrew Scott | Schedule Pre Construction Meeting | Yes | No
258642367951 | CT8208 (Lot 107 Te Whaiawa - 18 Kakaruai Crescent, West Melton) | CT8208 | Andrew Scott | Windows In | Yes | No
258566393311 | CT8207 (Lot 106 Te Whaiawa - 16 Kakaruai Crescent, West Melton) | CT8207 | Andrew Scott | Roof On | Yes | No
258635161033 | CT8206 (Lot 101 Te Whaiawa - 6 Kakaruai Crescent, West Melton) | CT8206 | Andrew Scott | Roof On | Yes | No
258644182518 | CT8172 (Lot 137 Prestons Grove - 26 Padstow Loop, Marshland, Christchurch) | CT8172 | Andrew Scott | Schedule Pre Construction Meeting | Yes | No
258577271281 | CT8167 (Lot 127 Prestons Grove - 46 Padstow Loop, Marshland, Christchurch) | CT8167 | Andrew Scott | Foundations / Slab Poured | Yes | No
258580865466 | CT8127 (Lot 134 Prestons Grove - 32 Padstow Loop, Marshland, Christchurch) | CT8127 | Andrew Scott | Foundations / Slab Poured | Yes | No
258562793932 | CT8007 (Lot 61 Hampton Grove - 11 Northampton Drive, Prebbleton) | CT8007 | Andrew Scott | Painting & Finishing | Yes | No
258705227246 | CT8006 (Lot 60 Hampton Grove - 13 Northampton Drive, Prebbleton) | CT8006 | Andrew Scott | Painting & Finishing | Yes | No
258541256158 | CT8447 (Lot 4 Berryfields - 147 Gardiners Road, Harewood) | CT8447 | Corey Flynn | Fixtures/Internal Fit Out | Yes | No
258644182517 | CT8446 (Lot 2 Berryfields - 151 Gardiners Road, Harewood) | CT8446 | Corey Flynn | Fixtures/Internal Fit Out | Yes | No
258580864505 | CT8166 (Lot 126 Prestons Grove - 48 Padstow Loop, Marshland, Christchurch) | CT8166 | Corey Flynn | Frames Up | Yes | No
258644182516 | CT8124 (Lot 125 Prestons Grove - 50 Padstow Loop, Marshland, Christchurch) | CT8124 | Corey Flynn | Frames Up | Yes | No
258544874997 | CT8587 (Lot 16 Sabys Estate - 36 Matamoe Drive, Halswell) | CT8587 | Fraser Finlayson | Roof On | Yes | No
258575424978 | CT8555 (Lot 31 Quaifes Park - 41 Cork Street, Halswell, Christchurch) | CT8555 | Fraser Finlayson | Interior Linings | Yes | No
258580864503 | CT8428 (Lot 13 Halswell Country Estates - 49 Podocarp Drive, Christchurch) | CT8428 | Fraser Finlayson | Customer Walkthrough & Final Inspection | Yes | No
258642367950 | CT8427 (Lot 12 Halswell Country Estates - 47 Podocarp Drive, Christchurch) | CT8427 | Fraser Finlayson | Fixtures/Internal Fit Out | Yes | No
258647787966 | CT8426 (Lot 11 Halswell Country Estates - 45 Podocarp Drive, Christchurch) | CT8426 | Fraser Finlayson | Fixtures/Internal Fit Out | Yes | No
258566393307 | CT8204 (Lot 18 Te Whaiawa - 56 Te Whaiawa Crescent, West Melton) | CT8204 | Fraser Finlayson | Cladding On | Yes | No
258580864502 | CT8203 (Lot 17 Te Whaiawa - 58 Te Whaiawa Crescent, West Melton, Selwyn) | CT8203 | Fraser Finlayson | Interior Linings | Yes | No
258544874995 | CT8200 (Lot 14 Te Whaiawa - 64 Te Whaiawa Crescent, West Melton) | CT8200 | Fraser Finlayson | Interior Linings | Yes | No
258553799140 | CT8197 (Lot 9 Te Whaiawa - 74 Te Whaiawa Crescent, West Melton) | CT8197 | Fraser Finlayson | Painting & Finishing | Yes | No
258642367949 | CT8196 (Lot 8 Te Whaiawa - 76 Te Whaiawa Crescent, West Melton) | CT8196 | Fraser Finlayson | Painting & Finishing | Yes | No
258645991883 | CT8587 (Lot 16 Sabys Estate - 36 Matamoe Drive, Halswell) | CT8587 | Fraser Finlayson | Roof On | Yes | No
258635160043 | CT8555 (Lot 31 Quaifes Park - 41 Cork Street, Halswell, Christchurch) | CT8555 | Fraser Finlayson | Interior Linings | Yes | No
258516061679 | CT8428 (Lot 13 Halswell Country Estates - 49 Podocarp Drive, Christchurch) | CT8428 | Fraser Finlayson | Customer Walkthrough & Final Inspection | Yes | No
258644182483 | CT8427 (Lot 12 Halswell Country Estates - 47 Podocarp Drive, Christchurch) | CT8427 | Fraser Finlayson | Fixtures/Internal Fit Out | Yes | No
258644182482 | CT8426 (Lot 11 Halswell Country Estates - 45 Podocarp Drive, Christchurch) | CT8426 | Fraser Finlayson | Fixtures/Internal Fit Out | Yes | No
258635160042 | CT8204 (Lot 18 Te Whaiawa - 56 Te Whaiawa Crescent, West Melton) | CT8204 | Fraser Finlayson | Cladding On | Yes | No
258645991877 | CT8203 (Lot 17 Te Whaiawa - 58 Te Whaiawa Crescent, West Melton, Selwyn) | CT8203 | Fraser Finlayson | Interior Linings | Yes | No
258642366950 | CT8200 (Lot 14 Te Whaiawa - 64 Te Whaiawa Crescent, West Melton) | CT8200 | Fraser Finlayson | Interior Linings | Yes | No
258644182479 | CT8197 (Lot 9 Te Whaiawa - 74 Te Whaiawa Crescent, West Melton) | CT8197 | Fraser Finlayson | Painting & Finishing | Yes | No
258516061676 | CT8196 (Lot 8 Te Whaiawa - 76 Te Whaiawa Crescent, West Melton) | CT8196 | Fraser Finlayson | Painting & Finishing | Yes | No
258644177347 | CT8587 (Lot 16 Sabys Estate - 36 Matamoe Drive, Halswell) | CT8587 | Fraser Finlayson | Roof On | Yes | No
258644177346 | CT8555 (Lot 31 Quaifes Park - 41 Cork Street, Halswell, Christchurch) | CT8555 | Fraser Finlayson | Interior Linings | Yes | No
258638765540 | CT8428 (Lot 13 Halswell Country Estates - 49 Podocarp Drive, Christchurch) | CT8428 | Fraser Finlayson | Customer Walkthrough & Final Inspection | Yes | No
258575416816 | CT8427 (Lot 12 Halswell Country Estates - 47 Podocarp Drive, Christchurch) | CT8427 | Fraser Finlayson | Fixtures/Internal Fit Out | Yes | No
258638765539 | CT8426 (Lot 11 Halswell Country Estates - 45 Podocarp Drive, Christchurch) | CT8426 | Fraser Finlayson | Fixtures/Internal Fit Out | Yes | No
258562787775 | CT8204 (Lot 18 Te Whaiawa - 56 Te Whaiawa Crescent, West Melton) | CT8204 | Fraser Finlayson | Cladding On | Yes | No
258635154881 | CT8203 (Lot 17 Te Whaiawa - 58 Te Whaiawa Crescent, West Melton, Selwyn) | CT8203 | Fraser Finlayson | Interior Linings | Yes | No
258644177345 | CT8200 (Lot 14 Te Whaiawa - 64 Te Whaiawa Crescent, West Melton) | CT8200 | Fraser Finlayson | Interior Linings | Yes | No
258645983696 | CT8197 (Lot 9 Te Whaiawa - 74 Te Whaiawa Crescent, West Melton) | CT8197 | Fraser Finlayson | Painting & Finishing | Yes | No
258642361821 | CT8196 (Lot 8 Te Whaiawa - 76 Te Whaiawa Crescent, West Melton) | CT8196 | Fraser Finlayson | Painting & Finishing | Yes | No

## Missing CRM Links
Has Customer — Missing Contact or Deal Association
These tickets are flagged 'Yes' for customer but have no Contact ID and/or no Deal ID in HubSpot. High data integrity risk.
Ticket ID | Ticket Name | Hummer Job # | Owner | Stage | Contact Present | Deal Present | Issue
258566393312 | CT8409 (Lot 3 Highsted - 70 Flaxmill Road, Casebrook) | CT8409 | Killian O'Neill | Cladding On | NO | NO | Missing Contact + Deal
258564590017 | CT8170 (Lot 130 Prestons Grove - 40 Padstow Loop, Marshland, Christchurch) | CT8170 | Andrew Scott | Foundations / Slab Poured | NO | NO | Missing Contact + Deal
258577271280 | CT8002 (Lot 51 Hampton Grove - 33 Northampton Drive, Prebbleton) | CT8002 | Andrew Scott | Painting & Finishing | NO | NO | Missing Contact + Deal
258705227245 | CT8280 (Lot 91 Wilfield - 71 Ridgeland Way, West Melton) | CT8280 | Corey Flynn | Interior Linings | NO | Yes | Missing Contact
258541256156 | CT8617 (Lot 17 Halswell Country Estates - 20 Podocarp Drive, Halswell) | CT8617 | Fraser Finlayson | WD Submitted to Council | NO | NO | Missing Contact + Deal
258544874996 | CT8554 (Lot 30 Quaifes Park - 39 Cork Street, Halswell, Christchurch) | CT8554 | Fraser Finlayson | Interior Linings | NO | NO | Missing Contact + Deal
258705226199 | CT8617 (Lot 17 Halswell Country Estates - 20 Podocarp Drive, Halswell) | CT8617 | Fraser Finlayson | WD Submitted to Council | NO | NO | Missing Contact + Deal
258553798129 | CT8554 (Lot 30 Quaifes Park - 39 Cork Street, Halswell, Christchurch) | CT8554 | Fraser Finlayson | Interior Linings | NO | NO | Missing Contact + Deal
258638765542 | CT8617 (Lot 17 Halswell Country Estates - 20 Podocarp Drive, Halswell) | CT8617 | Fraser Finlayson | WD Submitted to Council | NO | NO | Missing Contact + Deal
258562787776 | CT8554 (Lot 30 Quaifes Park - 39 Cork Street, Halswell, Christchurch) | CT8554 | Fraser Finlayson | Interior Linings | NO | NO | Missing Contact + Deal